## Version 1
Scrap Collector Version 1 (End of week 8) | Feature | Status | Assigned for
Login
Register
View profile
Update profile
Homeowner - post scrap
Homeowner & Colletor - call
Homeowner - View Booking request
Homeowner - View Notification when having booking request
Homeowner- Update post information
Homeowner - View post history
Homeowner - Delete post
Homeowner - Accomplish post
Homeowner - Review Collector
Collector - Search near-by post
Collector - Search latest post
Collector - View post detail
Collector -View booking response
Collector - View list of booking
Collector -View review from Homeowner
Thuật toán basic

## Week plan
Week 6 | Tuesday | Trang post scrap 4 trang bên Trang chủ của App Homeowner Trang notification JSON define của API
| Thursday | Hoàn thành xong giao diện App Homeowner
| Saturday | Hoàn thành xong giao diện App Collector Có API cho các feature Version 1 app Homeowner
Week 7 | Tuesday | Ráp 50% API của Homeowner (các feature trong Version 1)
| Thursday | Ráp xong API của Homeowner (các feature trong Version 1)
| Saturday | Ráp API theo dạng JSON cho Collector (các feature trong Version 1) Có API cho các feature Version 1 app Homeowner
Week 8 | Tuesday | Ráp 50% Api của Collector (các feature trong Version 1)
| Thursday | Ráp xong API của Collector (các feature trong Version 1)
| Saturday | Version 1 review