## ProductBacklog
PRODUCT BACKLOG
# | Item | Priority | Point | Status
1 | Draw Usecase Diagram | 3 | 30 | Done
2 | Draw ERD | 3 | 30 | Done
3 | Draw Physical Diagram | 3 | 30 | Done
4 | Draw UI Mockup | 1 | 10 | Done
6 | Implement UI to Prototype | 2 | 20 | Done
8 | Draw Class Diagram | 3 | 30 | Done
9 | Draw System Architecture Diagram | 2 | 20 | Done
10 | Draw Sequence Diagram | 3 | 30 | Done
9 | Draw Acitivity Diagram | 3 | 30 | Done
11 | Implement Base features | - | - | -
| Register | 4 | 40 | Done
| Login | 2 | 20 | Done
| View Profile | 2 | 20 | Done
| Update Profile | 2 | 20 | Done
| Logout | 1 | 10 | Done
12 | Implement Homeowner features | - | - | -
| Post scrap | 5 | 50 | Done
| View Booking request | 2 | 20 | Done
| Accept Booking request | 3 | 30 | Done
| Reject Booking request | 3 | 30 | Done
| View booked scrap | 3 | 30 | Done
| View notification | 2 | 20 | Done
| Chat to Collector | 2 | 20 | Done
| Report Collector | 2 | 20 | Done
| Review Collector | 3 | 30 | Done
| Implement Price Recommend price feature | 3 | 30 | Done
13 | Implement Collector features | - | - | -
| View nearby scraps | 3 | 30 | Done
| View latest scraps | 3 | 30 | Done
| View scrap detail | 3 | 30 | Done
| Book scrap | 3 | 30 | Done
| Negotiate price | 3 | 30 | Done
| View Booking request | 3 | 30 | Done
| Cancel booking request | 3 | 30 | Done
| View schedule | 4 | 40 | Done
| View direction to scrap's place | 3 | 30 | Done
| Chat to Homewowner | 2 | 20 | Done
| Call Homeowner | 2 | 20 | Done
| Report Homeowner | 1 | 10 | Done
| Report scrap | 1 | 10 | Done
14 | Implement Admin features | - | - | -
| View all scraps in the System | 2 | 20 | Done
| View all accounts in the System | 3 | 30 | Done
| View all categories in the System | 3 | 30 | Done
| View all scrap reports in the System | 2 | 20 | Done
| View all account reports in the System | 2 | 20 | Done
| Deactivate scrap | 2 | 20 | Done
| View scrap detail | 2 | 20 | Done
| View account detail | 2 | 20 | Done
| View scrap report | 2 | 20 | Done
| View account report | 2 | 20 | Done
15 | Research + Training | - | - | -
| React Native | 3 | 30 | Done
| React Redux | 3 | 30 | Done
| NestJS | 4 | 40 | Done
| Angular | 2 | 20 | Done
16 | Document | - | - | -
| Report 1 | 2 | 20 | Done
| Report 2 | 2 | 20 | Done
| Report 3 | 2 | 20 | Done
| Report 4 | 3 | 30 | Done
| Report 5 | 2 | 20 | Done
| Report 6 | 2 | 20 | Done
17 | Write System Test | - | - | -
| Write test case for base features | 2 | 20 | Done
| Write test case for Homeowner features | 3 | 30 | Done
| Write test case for Collector features | 3 | 30 | Done
| Write test case for Admin features | 3 | 30 | Done
18 | Implement System Test | - | - | -
| Implement test for base features | 2 | 20 | Done
| Implement test for Homeowner features | 3 | 30 | Done
| Implement test for Collector features | 3 | 30 | Done
| Implement test for Admin features | 3 | 30 | Done

## Sprint 1
a | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Draw ERD | Draw ERD | Duy Dat | DONE | 2 | 1 | 1 | 0 | 0 | 0 | Need to be checked and updated
Draw Physical Diagram | Draw Physical Diagram | Bao Khanh | DONE | 3 | 3 | 2 | 1 | 0 | 0
Draw Usecase Diagram | Draw Usecase diagram | Duy Dat | DONE | 4 | 4 | 3 | 2 | 1 | 0
Draw UI mockup | Basic function View | Hoang Nhan | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Homeowner View | Anh Trung | DONE | 1 | 1 | 1 | 0 | 0 | 0
| Collector View | Anh Trung | DONE | 1 | 1 | 0 | 0 | 0 | 0 | Need to be checked
| Admin Website View | Hoang Nhan | DONE | 1 | 1 | 1 | 0 | 0 | 0 | Need to be checked
Report 1 | Introduction, current situation | Duy Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Problem definition | Duy Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Proposed solution | Duy Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Functional requirement, role responsibility | Anh Trung | DONE | 1 | 1 | 0 | 0 | 0 | 0
Total

## Sprint 2
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Update ERD | Khanh | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Update Physical Diagram | Khanh | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Update mock UI | Nhan + Trung | DONE | 2 | 2 | 1 | 0 | 0 | 0
Research + Training | Document | Dat | DONE | 3 | 3 | 2 | 1 | 0 | 0
| React native | Dat | DONE | 3 | 3 | 2 | 1 | 0 | 0
|  | Khanh | DONE | 3 | 3 | 3 | 2 | 1 | 0
|  | Trung | DONE | 3 | 3 | 3 | 2 | 1 | 0
|  | Nhan | DONE | 3 | 3 | 3 | 2 | 2 | 1
| NestJS | Khanh | DONE | 2 | 2 | 1 | 0 | 0 | 0
| PostgreSQL | Khanh | DONE | 3 | 3 | 2 | 1 | 0 | 0
|  | Dat | DONE | 3 | 3 | 2 | 1 | 0 | 0
|  | Trung | DONE | 3 | 3 | 2 | 1 | 0 | 0
| Typescript | Khanh | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Firebase cloud message | Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Socket.io | Khanh | DONE | 2 | 2 | 1 | 0 | 0 | 0
| CI/CD by Gitlab | Khanh | DONE | 2 | 2 | 1 | 0 | 0 | 0
Implement UI to Prototype | Login Screen | Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Register screen | Trung | DONE | 1 | 1 | 1 | 0 | 0 | 0
| Profile screen | Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0 | Need to be checked
| Update profile screen | Nhan | DONE | 1 | 1 | 1 | 0 | 0 | 0 | Need to be checked
Report 2 | Problem definition | Dat | DONE | 1 | 1 | 0 | 0 | 0 | 0
| Project overview | Khanh | DONE | 1 | 1 | 1 | 0 | 0 | 0
| Project Organization | Trung | DONE | 1 | 1 | 1 | 1 | 0 | 0
| Coding convention | Nhan | DONE | 1 | 1 | 1 | 1 | 1 | 0 | Need to be checked
Total

## Sprint 3
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Review and check Report 2 | Duy Dat | Done | 2 | 2 | 1 | 0 | 0 | 0
Implement UI to prototype | Post scrap screen | Dat | Done | 2 | 2 | 1 | 0 | 0 | 0 | Need to be checked
| View booking request screen | Trung | Done | 2 | 2 | 2 | 1 | 0 | 0
| View accepted booking screen | Nhan | Done | 2 | 2 | 2 | 2 | 1 | 0
| Notification screen | Dat | Done | 2 | 2 | 2 | 1 | 0 | 0
| Chat screen | Trung | Done | 2 | 2 | 2 | 1 | 0 | 0
| Collector home screen | Nhan | Done | 2 | 2 | 2 | 1 | 0 | 0
| View scrap detail screen | Khanh | Done | 2 | 2 | 2 | 1 | 0 | 0
| Book scrap screen | Khanh | Done | 2 | 2 | 2 | 1 | 0 | 0
| View schedule screen | Dat | Done | 2 | 2 | 2 | 1 | 0 | 0
| View history screen | Trung | Done | 2 | 2 | 2 | 1 | 0 | 0
Implement API | Basic function API | Khanh | Done | 1 | 1 | 0 | 0 | 0 | 0 | Need to be checked
| Homeowner API | Nhan | Done | 3 | 3 | 2 | 1 | 0 | 0 | Need to be checked
Create database | Create Database | Khanh | Done | 1 | 1 | 0 | 0 | 0 | 0
| Deploy database to google cloud | Khanh | Done | 2 | 2 | 2 | 0 | 0 | 0
Report 3 | User requirement specification | Dat | Done | 1 | 1 | 1 | 0 | 0 | 0
| System requirement specification | Trung | Done | 1 | 1 | 0 | 0 | 0 | 0
| System overview use case | Dat | Done | 1 | 1 | 1 | 0 | 0 | 0
| Guest - Authorized User Use case specification | Nhan | Done | 2 | 2 | 2 | 1 | 0 | 0
| Homeowner Use case specification | Dat | Done | 2 | 2 | 2 | 1 | 0 | 0
| Collector Use case specification | Trung | Done | 2 | 2 | 0 | 0 | 0 | 0
| Admin Use case specification | Khanh | Done | 2 | 1 | 0 | 0 | 0 | 0
| Software system attribute | Dat | Done | 1 | 1 | 1 | 0 | 0 | 0
| Conceptual Diagram | Dat | Done | 2 | 2 | 2 | 1 | 1 | 0 | Need to be checked
Reseacrh Algorithm | Linear Regression | Trung | Done | 5 | 5 | 4 | 2 | 1 | 0
Total

## Sprint 4
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Review and check Report 3 | Duy Dat | Done | 4 | 3 | 2 | 1 | 0 | 0
| Update prototype | Nhan + Trung | Done | 3 | 3 | 2 | 1 | 0 | 0
Connect Api to User Interface | Basic function API | Dat | Done | 3 | 3 | 2 | 1 | 0 | 0
| Post scrap API | Nhan | Done | 3 | 3 | 2 | 1 | 0 | 0
| View booking request API | Trung | Done | 3 | 3 | 2 | 1 | 0 | 0
| Accept booking API | Dat | Done | 3 | 3 | 2 | 1 | 0 | 0
| Reject booking API | Dat | Done | 3 | 3 | 2 | 1 | 0 | 0
| View History API | Trung | Done | 3 | 3 | 2 | 1 | 0 | 0
| View profile API | Trung | Done | 3 | 3 | 2 | 1 | 0 | 0
| Update profile API | Dat | Done | 3 | 3 | 2 | 1 | 0 | 0
Implement API | Collector's features API | Khanh | Done | 3 | 3 | 2 | 1 | 0 | 0
| Web Admin's features API | Khanh | Done | 3 | 3 | 2 | 1 | 0 | 0
Inplement Linear Regression | Get Recommend price API | Dat | Done | 3 | 3 | 2 | 1 | 0 | 0
| Get Recommend price feature in mobile app | Trung | Done | 3 | 3 | 2 | 1 | 0 | 0
| Write document for Linear Regression Algorithm | Dat + Trung | Done | 3 | 3 | 2 | 1 | 0 | 0 | Need to be checked
Report 4 | System Architecture | Khanh | Done | 2 | 2 | 1 | 0 | 0 | 0
| System requirement specification | Khanh | Done | 2 | 2 | 0 | 0 | 0 | 0
| Component Diagram | Nhan | Done | 2 | 2 | 1 | 0 | 0 | 0
| Class Diagram | Trung | Done | 2 | 2 | 2 | 0 | 0 | 0
| Sequence Diagram | Dat | Done | 2 | 2 | 2 | 1 | 0 | 0
| Activity Diagram | Trung | Done | 2 | 2 | 2 | 0 | 0 | 0
| State machine Diagram | Nhan | Done | 2 | 2 | 1 | 0 | 0 | 0
| User Interface Design | Dat | Done | 2 | 2 | 1 | 0 | 0 | 0
| Algorithm | Trung | Done | 2 | 2 | 1 | 0 | 0 | 0 | Need to be checked
| Database design | Khanh | Done | 2 | 2 | 1 | 0 | 0 | 0
Total

## Sprint 5
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Review and check Report 4 | Duy Dat | Done | 4 | 2 | 1 | 0 | 0 | 0
Connect Api to User Interface | Search near by scrap | Duy Dat | Done | 4 | 3 | 2 | 1 | 1 | 0
| View scrap detail | Duy Dat | Done | 4 | 3 | 3 | 2 | 2 | 0
| Book scrap | Hoang Nhan | Done | 4 | 3 | 2 | 2 | 2 | 0
| Chat to Homeowner | Bao Khanh | Done | 4 | 3 | 2 | 1 | 1 | 0 | Need to be checked
| View schedule | Anh Trung | Done | 4 | 3 | 2 | 1 | 1 | 0 | Need to be checked
| Make review | Hoang Nhan | Done | 4 | 3 | 2 | 1 | 1 | 0
Implement Web Admin | Basic function API | Bao Khanh | Done | 4 | 3 | 2 | 1 | 1 | 0
| Web admin API | Hoang Nhan | Done | 4 | 3 | 2 | 1 | 1 | 0
|  | Anh Trung | Done | 4 | 3 | 2 | 1 | 1 | 0
Implement Testing | Write Test Plan | Hoang Nhan | Done | 4 | 3 | 2 | 1 | 1 | 0
| Write Test Case | Duy Dat | Done | 4 | 3 | 2 | 1 | 1 | 0
| Write Test Case in Japanese | Duy Dat + Hoang Nhan | Done | 4 | 3 | 2 | 1 | 1 | 0
Report 5 | Introduction | Bao Khanh | Done | 4 | 3 | 2 | 1 | 1 | 0
| Data relationship Diagram | Bao Khanh | Done | 4 | 3 | 2 | 1 | 1 | 0
| Technology, framework | Bao Khanh | Done | 4 | 3 | 2 | 1 | 1 | 0
| Test plan | Anh Trung | Done | 4 | 3 | 2 | 1 | 1 | 0
| Test case | Duy Dat | Done | 4 | 3 | 2 | 1 | 1 | 0
|  | Bao Khanh | Done | 4 | 3 | 2 | 1 | 1 | 0
|  | Hoang Nhan | Done | 4 | 3 | 2 | 1 | 1 | 0
|  | Anh Trung | Done | 4 | 3 | 2 | 1 | 1 | 0
Total

## Sprint 6
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Review and check Report 5 | Duy Dat | Done | 4 | 3 | 2 | 0 | 0 | 0
Implement testing mobile application | Test basic feature | Hoang Nhan | Done | 2 | 2 | 1 | 0 | 0 | 0
| Test Homeowner's features | Hoang Nhan | Done | 2 | 2 | 2 | 1 | 0 | 0
| Test Collector's features | Anh Trung | Done | 2 | 2 | 2 | 0 | 0 | 0
| Test notification | Bao Khanh | Done | 1 | 1 | 1 | 0 | 0 | 0
Implement testing web admin | Write test case for web admin | Hoang Nhan | Done | 1 | 1 | 1 | 0 | 0 | 0
| Do the test | Duy Dat | Done | 2 | 2 | 1 | 0 | 0 | 0
Report 6 | Installation Guide | Duy Dat | Done | 2 | 2 | 1 | 0 | 0 | 0
|  | Bao Khanh | Done | 2 | 2 | 1 | 0 | 0 | 0
|  | Hoang Nhan | Done | 2 | 2 | 1 | 0 | 0 | 0
|  | Anh Trung | Done | 2 | 2 | 1 | 0 | 0 | 0
| User Guide | Duy Dat | Done | 2 | 2 | 1 | 0 | 0 | 0
|  | Bao Khanh | Done | 2 | 2 | 1 | 0 | 0 | 0
|  | Hoang Nhan | Done | 2 | 2 | 1 | 0 | 0 | 0
|  | Anh Trung | Done | 2 | 2 | 1 | 0 | 0 | 0
| Report 6 in Japanese | Duy Dat | Done | 3 | 2 | 1 | 0 | 0 | 0
|  | Hoang Nhan | Done | 3 | 3 | 2 | 1 | 0 | 0
Total

## Sprint 7
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Review and check Report 6 | Duy Dat | Done | 4 | 2 | 0 | 0 | 0 | 0
Prepare for Review | Overview test the system | Duy Dat | Done | 7
|  | Bao Khanh | Done | 7
|  | Hoang Nhan | Done | 7
|  | Anh Trung | Done | 7
Prepare slide | Prepare silde for presentation | Duy Dat | WORKING | 4
|  | Bao Khanh | WORKING | 4
Total