## ProductBacklog
PRODUCT BACKLOG
# | Item | Priority | Point | Status
1 | Draw Usecase Diagram | 3 | 30 | Done
2 | Draw ERD | 3 | 30 | Done
3 | Draw Physical Diagram | 3 | 30 | Done
4 | Draw UI Mockup | 1 | 10 | Done
6 | Implement UI to Prototype | 2 | 20 | Done
8 | Draw Class Diagram | 3 | 30 | Done
9 | Draw System Architecture Diagram | 2 | 20 | Done
10 | Draw Sequence Diagram | 3 | 30 | Done
9 | Draw Acitivity Diagram | 3 | 30 | Done
11 | Implement Base features | - | - | -
| Register | 4 | 40 | Done
| Login | 2 | 20 | Done
| View Profile | 2 | 20 | Done
| Update Profile | 2 | 20 | Done
| Logout | 1 | 10 | Done
12 | Implement Homeowner features | - | - | -
| Post scrap | 5 | 50 | Done
| View Booking request | 2 | 20 | Done
| Accept Booking request | 3 | 30 | Done
| Reject Booking request | 3 | 30 | Done
| View booked scrap | 3 | 30 | Done
| View notification | 2 | 20 | Done
| Chat to Collector | 2 | 20 | Done
| Report Collector | 2 | 20 | Done
13 | Implement Collector features | - | - | -
| View nearby scraps | 3 | 30 | Done
| View latest scraps | 3 | 30 | Done
| View scrap detail | 3 | 30 | Done
| Book scrap | 3 | 30 | Done
| Negotiate price | 3 | 30 | Done
| View Booking request | 3 | 30 | Done
| Cancel booking request | 3 | 30 | Done
| View schedule | 3 | 30 | Done
| View direction to scrap's place | 3 | 30 | Done
| Chat to Homewowner | 2 | 20 | Done
| Call Homeowner | 2 | 20 | Done
14 | Implement Admin features | - | - | -
| View all scraps in the System | 2 | 20 | Done
| View all accounts in the System | 3 | 30 | Done
| View all categories in the System | 3 | 30 | Done
View all scrap reports in the System
View all account reports in the System
Deactivate scrap
View scrap detail
View account detail
15 | Research + Training | - | - | -
| React Native | 3 | 30 | Done
| React Redux | 3 | 30 | Done
| NestJS | 4 | 40 | Done
| Angular | 2 | 20 | Done
16 | Document | - | - | -
| Report 1 | 2 | 20 | Done
| Report 2 | 2 | 20 | Done
| Report 3 | 2 | 20 | Done
| Report 4 | 3 | 30 | Done
| Report 5 | 2 | 20
| Report 6 | 2 | 20
17 | Write System Test | - | - | -
| Write test case for base features | 2 | 20 | Done
| Write test case for Homeowner features | 3 | 30 | Done
| Write test case for Collector features | 3 | 30 | Done
| Write test case for Admin features | 3 | 30 | Done
18 | Implement System Test | - | - | -
| Implement test for base features | 2 | 20 | Done
| Implement test for Homeowner features | 3 | 30 | Done
| Implement test for Collector features | 3 | 30 | Done
| Implement test for Admin features | 3 | 30 | Done

## Sprint 1
a | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Draw ERD | Draw ERD
Draw Physical Diagram | Draw Physical Diagram
Draw Usecase Diagram | Draw Usecase diagram
Draw UI mockup | Quality Tester View
Experience Tester View
Technology Tester View
Content Tester View
Result + Report View
Report 1 | Introduction, current situation
Problem definition
Proposed solution
Functional requirement, role responsibility
Total

## Sprint 2
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable
Research + Training
Implement UI to Prototype
Report 2
Total

## Sprint 3
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Update ERD |  | Done | 4 | 2 | 0 | 0 | 0 | 0
| Total |  |  | 160 | 128 | 96 | 72 | 40 | 0