## ProductBacklog
PRODUCT BACKLOG
# | Item | Priority | Point | Status
1 | Draw Usecase Diagram | 3 | 30 | Done
2 | Draw ERD | 3 | 30 | Done
3 | Draw Physical Diagram | 3 | 30 | Done
4 | Draw UI Mockup | 1 | 10 | Done
6 | Implement UI to Prototype | 2 | 20 | Done
8 | Draw Class Diagram | 3 | 30
9 | Draw System Architecture Diagram
10 | Draw Sequence Diagram
9 | Draw Acitivity Diagram | 3 | 30
11 | Implement Base features | - | - | -
| Register | 4 | 40 | Done
| Login | 2 | 20 | Done
View Profile
Update Profile
| Logout | 2 | 20 | Done
12 | Implement Homeowner features | - | - | -
|  | 5 | 50
|  | 5 | 50
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 5 | 50
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
|  | 3 | 30
13 | Implement Collector features
14 | Implement Admin features | - | - | -
|  | 2 | 20
|  | 3 | 30
|  | 3 | 30
15 | Research + Training | - | - | -
| React Native | 3 | 30 | Done
| React Redux | 3 | 30 | Done
16 | Document | - | -
| Report 1 | 2 | 20 | Done
| Report 2 | 2 | 20 | Done
| Report 3 | 2 | 20
| Report 4 | 2 | 20
| Report 5 | 2 | 20
| Report 6 | 2 | 20
17 | System Test

## Sprint 1
a | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Draw ERD | Draw ERD
Draw Physical Diagram | Draw Physical Diagram
Draw Usecase Diagram | Draw Usecase diagram
Draw UI mockup | Quality Tester View
Experience Tester View
Technology Tester View
Content Tester View
Result + Report View
Report 1 | Introduction, current situation
Problem definition
Proposed solution
Functional requirement, role responsibility
Total

## Sprint 2
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable
Research + Training
Implement UI to Prototype
Report 2
Total

## Sprint 3
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Fix previous deliverable | Update ERD | ViNTT | Done | 4 | 2 | 0 | 0 | 0 | 0
| Total |  |  | 160 | 128 | 96 | 72 | 40 | 0

## Sprint 4
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Research | Selenium, Jsoup Research | AnhTP | Done | 8 | 0 | 0 | 0 | 0 | 0
| PhantomJS Research | TrinhND | Done | 8 | 0 | 0 | 0 | 0 | 0
Implement Spelling Test | Optimize with error weight of a node, max error weight on entire branch | ViNTT | Done | 8
Optimize Sitemap | Categorize link: internal and external type | ViNTT | Done | 4
| List pages together link to one page | ViNTT | Done | 4
| Generate decode list from graph | ViNTT | Done | 4
Using Canvas for drawing Sitemap | Traverse in decode graph | ViNTT | Done | 8
| Calculate distance, element's attribute | ViNTT | Done | 8
| Draw sample | ViNTT | Done | 4
Implement Page Test | Get HTTP code for each page | AnhTP | Done | 4 | 4 | 0 | 0 | 0 | 0
| Get title for each page | AnhTP | Done | 3 | 3 | 0 | 0 | 0 | 0
| Binding data on UI | AnhTP | Done | 5 | 5 | 4 | 0 | 0 | 0
| Get canonical url for each page | AnhTP | Done | 5 | 5 | 5 | 1 | 0 | 0
Implement Redirection Test | Get Message Respone for each page | AnhTP | Done | 5 | 5 | 5 | 5 | 0 | 0
| Get URL redirection to | AnhTP | Done | 5 | 5 | 5 | 5 | 3 | 0
| Binding data on UI | AnhTP | Done | 5 | 5 | 5 | 5 | 5 | 0
Implement Speed Test | Get url, interacticve time, pageload time | TrinhND | Done | 8 | 8 | 0 | 0 | 0 | 0
| Demo binding data to UI | TrinhND | Done | 4 | 4 | 4 | 0 | 0 | 0
| Get page size | TruongLN | Done | 8
| Binding data to UI | TruongLN | Done | 4
| Binding average data to UI | TrinhND | Done | 4 | 4 | 4 | 0 | 0 | 0
Implement JavaScript Error Test | Demo get JS Error with chromeDriver, Phantomjs | TrinhND | Done | 4 | 4 | 4 | 4 | 0 | 0
| Get error message, type, page affected | TrinhND | Done | 10 | 10 | 10 | 10 | 6 | 0
| Binding data to UI | TruongLN | Done | 8
Implement other support functions | Fix UI : Favicon page, mobile layout page | TrinhND | Done | 2 | 2 | 2 | 2 | 2 | 0
| Save temporary result test to DB | TruongLN | Done | 4
| Deloy Azure Service | TruongLN | Done | 8
| Implement Multiple Thread | TruongLN | Done | 8

## Spint5
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Fix previous deliverable | Update ERD - Add 15 Type-Report Entities + Fix relationships | ViNTT | Done | 4
Design Database | Design Database + POJO in Java | TruongLN | Done | 16
Optimize Sitemap | Handle exception with error page | ViNTT | Done | 2
| Binding Value on Sitemap Screen | ViNTT | Done | 6
| Get coordinate at mouse click | ViNTT | Done | 6
| Get each rectangle's coordinate of sitemap | ViNTT | Done | 6
| Mouseclick event handling for pop-up: Pages referencing to a same page | ViNTT | Done | 8
| Decorate Sitemap to recognize internal, external, error link | ViNTT | Done | 8
Implement Contact Details Test | Define regular expression | AnhTP | Done | 2 | 0 | 0 | 0 | 0 | 0
| Get phone number on the website | AnhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
| Get email on the website | AnhTP | Done | 4 | 2 | 0 | 0 | 0 | 0
| Binding data on UI | AnhTP | Done | 3 | 3 | 0 | 0 | 0 | 0
Implement Missing File Test | Define regular expression | AnhTP | Done | 4 | 4 | 1 | 0 | 0 | 0
| Parse to get tag <img> for each page | AnhTP | Done | 6 | 6 | 6 | 0 | 0 | 0
| Parse to get tag Video for each page | AnhTP | Done | 4 | 4 | 4 | 3 | 0 | 0
| Parse to get tag Audio for each page | AnhTP | Done | 3 | 3 | 3 | 3 | 0 | 0
| Parse to get tag Link for each page | AnhTP | Done | 4 | 4 | 4 | 4 | 2 | 0
| Get http code for each src and href | AnhTP | Done | 3 | 3 | 3 | 3 | 3 | 0
| Binding data on UI | AnhTP | Done | 3 | 3 | 3 | 3 | 3 | 0
Implement Broken Link Test | Get internal, external link for each page from Sitemap | TrinhND | Done | 4 | 0 | 0 | 0 | 0 | 0
| Get Get HTTP code for each link | TrinhND | Done | 4 | 0 | 0 | 0 | 0 | 0
| Get all the broken links | TrinhND | Done | 4 | 4 | 0 | 0 | 0 | 0
| Binding data on UI | TrinhND | Done | 4 | 4 | 0 | 0 | 0 | 0
| Catch exceptions and fix error responses | TrinhND | Done | 4 | 4 | 4 | 0 | 0 | 0
Implement Broken Page Test | Get all pages of the website from the Sitemap | TrinhND | Done | 4 | 4 | 4 | 0 | 0 | 0
| Get HTTP code, status for each page | TrinhND | Done | 4 | 4 | 4 | 4 | 0 | 0
| Get all the broken pages | TrinhND | Done | 4 | 4 | 4 | 4 | 0 | 0
| Binding data on UI | TrinhND | Done | 4 | 4 | 4 | 4 | 4 | 0
| Catch exceptions and fix error responses | TrinhND | Done | 4 | 4 | 4 | 4 | 4 | 0
Implement Server Behavior Test | Handle URLs with a www prefix and redirect to a non-www prefix wherever possible | TruongLN | Done | 8
| Redirect non-SSL pages to SSL pages | TruongLN | Working in progress | 8 |  |  |  |  | 6
| Check page which use SSL | TruongLN | Working in progress | 8 |  |  |  |  | 6
|  | Total |  | 160

## Sprint 6
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Implement Server Behavior Test | Redirect non-SSL pages to SSL pages | TruongLN | Done | 6 | 0 | 0 | 0 | 3 | 3
| Check page which use SSL | TruongLN | Done | 6 | 2 | 0 | 0 | 0 | 2
| Binding data on UI | TruongLN | Done | 3 | 0 | 0 | 0 | 0 | 3
Implement Favicon Test | Test case: Use of a rel attribute value defined in a profile | AnhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
| Test case: Putting the favicon at a predefined URI | AnhTP | Done | 6 | 2 | 0 | 0 | 0 | 0
| Get Favicon for each page with input root | AnhTP | Done | 5 | 5 | 0 | 0 | 0 | 0
| Catch exceptions and fix error responses | AnhTP | Done | 3 | 3 | 2 | 0 | 0 | 0
Implement Cookie Test | Get List of cookie of each page | TrinhND | Done | 4 | 0 | 0 | 0 | 0 | 0
| Get Name, get domain, get example value, get expiry date of each cookie | TrinhND | Done | 8 | 4 | 0 | 0 | 0 | 0
| Catch exceptions and fix error responses | TrinhND | Done | 4 | 4 | 0 | 0 | 0 | 0
| Binding data on UI | TrinhND | Done | 2 | 2 | 2 | 0 | 0 | 0
Implement Sitemap | Design Sitemap Screen | ViNTT | Done | 4
| Mapping DTO | ViNTT | Done | 3
| Binding data on UI | ViNTT | Done | 4
Update + Optimize functions | Upgrade UI for alll screens | TruongLN | Done | 8 | 0 | 8 | 0 | 0 | 0
| Add using token and cookie for each user when login | TruongLN | Done | 8 | 0 | 0 | 8 | 0 | 0
| Page Options design and implement | TruongLN | Done | 5 | 0 | 0 | 0 | 5 | 0
| Upgrade UI for JavaScriptErrors | TruongLN | Done | 4 | 0 | 0 | 0 | 0 | 0
Report 3 | User Requirement Specification | AnhTP | Done | 2 | 2 | 2 | 0 | 0 | 0
| System Requirement Specification | TrinhND | Done | 4 | 4 | 4 | 0 | 0 | 0
| System Overview Use Case | ViNTT | Done | 4
| Software System Attribute | ViNTT | Done | 3
| Conceptual Diagram | ViNTT | Done | 4
| List of Use Case | - | - | - | - | - | - | - | -
| Login | ViNTT | Done | 2
| Test missing files (guest) | ViNTT | Done | 2
| Test broken links (guest) | ViNTT | Done | 2
| Build sitemap | ViNTT | Done | 3
| Synchronize data | ViNTT | Done | 3
| View pages referencing on the same page. | ViNTT | Done | 2
| Test spelling for website’s content. | ViNTT | Done | 3
| Test grammar for website’s content. | ViNTT | Done | 2
| Test prohibited for website’s content. | ViNTT | Not started | 2
| Test broken links. | TrinhND | Done | 2 | 2 | 2 | 0 | 0 | 0
| Test broken pages. | TrinhND | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test missing files. | AnhTP | Done | 4 | 4 | 4 | 0 | 0 | 0
| Test the mobile layout. | TrinhND | Done | 2 | 2 | 2 | 2 | 0 | 0
| Measure the speed test. | TrinhND | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test JavaScript errors. | TrinhND | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test Favicon. | AnhTP | Done | 4 | 4 | 4 | 4 | 0 | 0
| Test cookie website using. | TrinhND | Done | 2 | 2 | 2 | 2 | 2 | 0
| Test server behaviour. | TrinhND | Done | 2 | 2 | 2 | 2 | 2 | 0
| Test contact details on the website. | AnhTP | Done | 4 | 4 | 4 | 4 | 0 | 0
| Test redirections. | AnhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| Test website’s pages. | AnhTP | Done | 4 | 4 | 4 | 4 | 4 | 0
| Create report. | TrinhND | Done | 2 | 2 | 2 | 2 | 2 | 0
| View history reports. | TrinhND | Done | 2 | 2 | 2 | 2 | 2 | 0
| Manage staff permissions. | ViNTT | Not started | 2
| Manage the website’s dictionary. | ViNTT | Not started | 2
| Manage the warning word list. | ViNTT | Not started | 2
| View all reports. | ViNTT | Not started | 2
|  | Total |  | 171

## Sprint 7
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Optimize Missing File Test | Implement get size of file | AnhTP | Done | 4 | 0 | 0 | 0 | 0 | 0
| Dynamically searching with specific file format input | AnhTP | Done | 6 | 2 | 0 | 0 | 0 | 0
| Binding data on UI | AnhTP | Done | 4 | 4 | 0 | 0 | 0 | 0
Optimize Cookie Test | Research about cookie law(EU Cookie Law) | TrinhND | Done | 8 | 0 | 0 | 0 | 0 | 0
| Add a list of common cookie law | TrinhND | Done | 4 | 4 | 0 | 0 | 0 | 0
| Get CookieName , category, party, Description of each cookie | TrinhND | Done | 8 | 8 | 4 | 0 | 0 | 0
| Bindind data on UI | TrinhND | Done | 4 | 4 | 4 | 0 | 0 | 0
Optimize with the latest models | Mapping json | TruongLN | Done | 4 | 0 | 0 | 0 | 0 | 0
| Add Constant class | TruongLN | Done | 2 | 0 | 0 | 0 | 0 | 0
| Normalize models follow on the latest ERD | TruongLN | Done | 8 | 8 | 0 | 0 | 0 | 0
| Transfer all models related to response - request to package POJO | TruongLN | Done | 4 | 4 | 4 | 4 | 0 | 0
| Website dropdown option list with the specific user | TruongLN | Done | 4 | 2 | 0 | 0 | 0 | 0
| Fix stackoverflow error which make responses become the infinite json | TruongLN | Done | 4 | 4 | 4 | 4 | 0 | 0
Implement Spelling Test | Optimize TrieTree | ViNTT | Done
| Generate the dictionary into a text file for testing | ViNTT | Done
| Measure, compare alternative solutions | ViNTT | Done
| Search spelling mistakes: Wrong character case | ViNTT | Done
| Search spelling mistakes: Missing character case | ViNTT | Done
| Search spelling mistakes: Redundant character case | ViNTT | Done
| Using recursion + apply directly on TrieTree for searching mistakes | ViNTT | Done
| Using recursion + apply directly on TrieTree for suggesting results | ViNTT | Done
Fix bugs | Fix conflicts source code on Git | TruongLN | Done | 4 | 4 | 4 | 4 | 4 | 0
Report 3 | Manage staff permissions. | ViNTT | Done
| Manage the website’s dictionary. | ViNTT | Done
| Manage the warning word list. | ViNTT | Done
| View all reports. | ViNTT | Done
Report 4 | System Architectural Design | TruongLN | Done | 4 | 4 | 4 | 4 | 4 | 0
| Class Diagram | TruongLN | Done | 6 | 6 | 0 | 0 | 0 | 0
| Class Diagram Explanation | AnhTP | Done | 4 | 4 | 2 | 0 | 0 | 0
| ERD: Update ERD with new entities: Version, SiteMap + Fix relationships | ViNTT | Done
| Data Dictionary | TrinhND |  | 6 | 6 | 6 | 6 | 0 | 0
| Interaction Diagram | - | - | - | - | - | - | - | -
| Login | AnhTP | Done | 4 | 4 | 4 | 0 | 0 | 0
| Test broken links. | TrinhND |  | 2
| Test broken pages. | TrinhND |  | 2 | 2 | 2 | 2 | 0 | 0
| Test missing files. | AnhTP | Done | 2 | 2 | 2 | 0 | 0 | 0
| Measure the speed test. | AnhTP | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test JavaScript errors. | TrinhND |  | 2 | 2 | 2 | 2 | 2 | 0
| Test Favicon. | AnhTP | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test cookie website using. | TrinhND |  | 2 | 2 | 2 | 2 | 2 | 0
| Test server behaviour. | TrinhND |  | 2 | 2 | 2 | 2 | 2 | 0
| Test contact details on the website. | AnhTP | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test redirections. | AnhTP | Done | 2 | 2 | 2 | 2 | 0 | 0
| Test website’s pages. | AnhTP | Done | 2 | 2 | 2 | 2 | 2 | 0
| Create report. | AnhTP | Done | 2 | 2 | 2 | 2 | 2 | 0
| View history reports. | AnhTP | Done | 2 | 2 | 2 | 2 | 2 | 0
| View all reports | AnhTP | Done | 2 | 2 | 2 | 2 | 2 | 0

## Sprint 8
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Update source code with changes in permission of each role | Permission Route | TruongLN
| Move Setting to Manager UI | TruongLN
| Add manager by role, and the relation manager and staff | TruongLN
Optinmize source code | Update model entity | TruongLN
| Optimize for manager screen | TruongLN
| System authentication | TruongLN
| Make version of sitemap more faster | TruongLN
| Permision several time for better performance | TruongLN
| Preprocessing the input data for test | TruongLN
Fix Bug | Fix bugs | TruongLN
Implement Staff feature | Screen Page Option for staff | TruongLN
Report 3 | Review, fix and update with new changes in roles | ViNTT |  | 8
| Update Business Rule in each use case specification | ViNTT |  | 8
| Synchronize data (manager) | AnhTP
| View pages referencing on the same page. (manager) | AnhTP
| Test grammar for website’s content. (staff) | AnhTP
| Test prohibited for website’s content. (staff) | AnhTP
| Manage the website’s dictionary. (manager) | AnhTP
| Manage the warning word list. (manager) | AnhTP
Report 4 | Algorithm | ViNTT |  | 16
| Component Diagram | ViNTT |  | 8

## Sprint 9
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5